PROGRAM: Cercetare de Excelenta (CEEX)

NUME PROIECT: Promovarea cercetarii in automatica si robotica in scopul integrarii in retele europene si internationale de cercetare

Acronim: PARSIR

Numar de inregistrare la Universitate / Data contract: 3C/27.01.2006

Modul: III

Director proiect: conf.dr.ing. Dorin Popescu

Parteneri: Universitatea din Craiova

Data incepere / finalizare proiect: 30.01.2006 - 1.12.2007

Valoarea proiectului: 195149 RON

Rezumat:

Proiectul isi propune cresterea vizibilitatii internationale a colectivului de cercetare, precum si integrarea sa in retele europene si internationale de cercetare. Obiectivele proiectului:

- realizarea de parteneriate S/T intre centrele de cercetare ale departamentului si structuri de cercetare similare internationale

- participarea ca membru in reteaua EURON (European Robotics Research Network), respectiv EIE-Surveyor

- organizarea la Craiova a conferintelor EAEEIE 2006, SINTES 2007 si pregatirea conferintei ICCC 2008, Craiova

- invitarea unor personalitati straine (profesori, cercetatori)

- participarea la pregatirea (realizarea) propunerilor de proiecte pe programe europene si internationale

- realizarea de sesiuni invitate la conferinte internationale

- constructia unui site web care sa permita participantilor sa se conecteze in permanenta la retele de cercetare-dezvoltare; infiintarea unui jurnal online, care sa publice unele lucrari selectate de la conferinte si/sau articole/ materiale de promovare, conform scopurilor proiectului

- participarea la activitati suport organizate in tara si in strainatate

ETAPELE PROIECTULUI SI DATELE DE PREDARE:
1. Organizarea unor intalniri stiintifice internationale. 1.07.2006; 51.649 RON.

2. Activitati suport pentru realizarea de acorduri de colaborare/parteneriat. 1.12.2006; 41.500 RON.

3. Activitati suport pentru integrarea in retele de cercetare. 1.06.2007; 51.100 RON.

4. Consolidarea parteneriatelor de cercetare. 1.12.2007; 50.900 RON.

PROGRAMME: CEEX

Name of the project: Promoting Romanian Automation and Robotics Research for Integration in European and International Research Networks

acronym: PARSIR

University Registration Number / Contract date: 3C/27.01.2006

Module: III

Director of project: Assoc. Prof. PhD. Eng. Dorin Popescu

Partners: University of Craiova

Period: 30.01.2006 - 1.12.2007

Budget: 195149 RON

Summary:

Project’s aim is the international recognition of this research team, as well as its integration in international and European research networks. Project’s objectives are:

- the realization of S/T partnerships between department’s research team and similar international research structures;

- participation as a member in EURON (European Robotics Research Network) and EIE-Surveyor networks;

- organization of EAEEIE 2006 and SINTES 2007 conferences at Craiova, and the preparation of International Carpathian Control Conference, 2008, Craiova;

- invitation of foreign personalities to participate to this kind of events;

- participation in preparation of projects proposals for international and European programmes;

- organization of invited sessions to international conferences;

- achievement of a website in order to allow to the participants to permanently keep in touch with the research – development networks; development of an online journal, to publish proceedings and/or promotion papers/materials, according to the project’s objectives;

- participation at national and international support activities.

SCHEDULE AND REPORT DEADLINES:
1. Organization of international scientific meetings. 1.07.2006; 51.649 RON.

2. Support activities for the achievement of co-operation/partnership agreements. 1.12.2006; 41.500 RON.

3. Support activities for integration in research networks. 1.06.2007; 51.100 RON.

4. Consolidation of research partnerships. 1.12.2007; 50.900 RON.