PROGRAM: CEEX

NUME PROIECT: DEZVOLTAREA INFRASTRUCTURII LABORATORULUI DE ANALIZE PENTRU SIGURANŢA ŞI CALITATEA PRODUSELOR AGROALIMENTARE LA NIVELUL CERINŢELOR DIRECTIVELOR UE ÎN DOMENIUL EVALUĂRII CONFORMITĂŢII

Acronim: CALITPROD

Numar de inregistrare la Universitate / Data contract: 28C/12.07.2006

Modul:  IV

Director proiect: Conf.univ.dr. Nour Violeta

Parteneri: -

Data incepere / finalizare proiect: 1.08.2006 – 31.01.2008

Valoarea proiectului: 800000 RON

Rezumat:

Proiectul propune alinierea metodelor de analize fizico-chimice impuse prin reglementări europene armonizate (Reg. EC 466/2001, 2002/26/EC, 94/35/EC) referitoare la siguranţa şi calitatea produselor agroalimentare şi la exactitatea necesară metodelor de încercare aplicate pentru evaluarea calităţii produselor alimentare prin controlul anumitor contaminanţi şi aditivi, astfel:

- determinarea metalelor grele şi toxice (cadmiu, plumb, mercur, staniu) prin spectrofotometrie şi spectrometrie de absorbţie atomică

- determinarea îndulcitorilor (aspartam, zaharină şi acesulfam K) prin cromatografie lichidă de înaltă performanţă

- determinarea acidului benzoic prin cromatografie lichidă de înaltă performanţă

De asemenea, proiectul propune acreditarea laboratorului de analize fizico-chimice la produsele agroalimentare, în conformitate cu cerinţele standardului SR EN ISO/CEI 17025/2005 "Cerinţe generale pentru competenţa laboratoarelor de încercări şi etalonări", ce are ca obiectiv asigurarea evaluării conformităţii. Proiectul se încadrează cerinţelor pentru asigurarea liberei circulaţii a produselor şi serviciilor, cu componenta sa de bază acreditarea, cuprinse în programul de negociere pentru aderare a României în Uniunea Europeană.

Proiectul contribuie la creşterea numărului de noi organisme din infrastructura calităţii şi, respectiv, la creşterea numărului de specialişti formaţi pe probleme de calitate. Laboratorul care urmează să fie acreditat prin proiect face parte din categoria organismelor insuficient reprezentate în infrastructura de evaluare a conformităţii, respectiv laboratoare de analize contaminanţi şi aditivi în produsele alimentare.

ETAPELE PROIECTULUI SI DATELE DE PREDARE

1. 1.08.2006 – 31.12.2006, Evaluarea performanţelor şi conformităţii metodelor de încercare fizico-chimice existente / necesare transpunerii directivelor şi reglementărilor europene şi pregătirea în domeniul calităţii Valoare – 420867 RON

2. 1.01.2007 – 31.07.2007, Dezvoltarea/ asimilarea metodelor de încercare şi demonstrarea capabilităţii laboratorului de încercări; Experimentarea şi dezvoltarea metodelor, Valoare – 321000 RON

3. 1.08.2007 – 30.09.2007, Confirmarea capabilităţilor laboratorului, implementarea, iniţierea acreditării metodelor de încercare, Valoare – 38133 RON

4. 1.10.2007 – 31.01.2008, Acreditarea laboratorului, Valoare – 20000 RON

PROGRAMME: CEEX

Name of the project: INFRASTRUCTURE′S DEVELOPMENT OF THE ANALYSIS LABORATORY FOR THE FOOD PRODUCTS SAFETY AND QUALITY AT THE LEVEL OF THE UE DIRECTIVES REQUIREMENTS IN THE FIELD OF THE CONFORMITY EVALUATION

acronym: CALITPROD

University Registration Number / Contract date: 28C/12.07.2006

Module :      IV

Director of project: Conf.univ.dr. Nour Violeta

Partners: -

Period: 1.08.2006 – 31.01.2008

Budget: 800000 RON

Summary:

The project proposes the adoption of the physical-chemical analysis methods imposed by the harmonized European Regulations concerning the safety and the quality of the food products and the accuracy needed for the analysis methods used for the evaluation of the food products quality through the control of some contaminants and additives, as following:

- determination of the heavy and toxic metals (Cd, Pb, Hg, Sn) through spectrophotometry and atomic absorption spectrometry;

- determination of some sweeteners (aspartame, sodium saccharin, acetsulfame-K) through high performance liquid chromatographic method;

- determination of the benzoic acid through high performance liquid chromatographic method.

Also, the project proposes the laboratory accreditation for these physical-chemical analysis, in concordance with the requirements of the SR EN ISO/CEI 17025/2005 "General requirements of testing and calibration laboratories", which has as objective the ensurance of the food products conformity evaluation.

The project contributes at the number increase of the new organisms from the quality understructure and respectively at the number increase of the specialists trained on the quality problems.

SCHEDULE AND REPORT DEADLINES
1. 1.08.2006 – 31.12.2006, Evaluation of the performance and conformity of the existing physical-chemical analysis methods needed for the transposition of the European Directives and Regulations and the training in the quality field, Value – 420867 RON

2. 1.01.2007 – 31.07.2007, Development/assimilation of the analysis methods and demonstration of the laboratory capability; Methods experimentation and development, Value – 321000 RON

3. 1.08.2007 – 30.09.2007, Confirmation of the laboratory capability, initiation of the analysis methods accreditation, Value – 38133 RON

4. 1.10.2007 – 31.01.2008, Laboratory accreditation, Value – 20000 RON