PROGRAM: CEEX  P-CD

NUME PROIECT :

Managementul individualizat al  recuperarii mobilitatii  pacientilor cu patologie neurologica  si ortopedica prin prisma unor metodologii de cercetare interdisciplinare

Acronim: MANMOBREC

Numar de inregistrare la Universitate / Data contract: 107/2006

Modul : I

Director proiect:  Avramescu Taina

Parteneri:  Spitalul Clinic de Urgenta MS  Curie, UMF Carol Davila, Universitatea Politehnica Bucuresti, IPA Bucuresti

Data incepere / finalizare proiect: 01/08/2006- 01/08/2008

Valoarea proiectului: 1 469 550 RON

Rezumat:

Proiectul isi propune sa  realizeze studiul motricitatii umane in conditii normale si patologice (patologie  ortopedico-traumatica si neurologica) prin crearea unui laborator de analiza a motricitatii umane in cadrul caruia, prin studii interdisciplinare, sa se reuseasca elaborarea unor fise de evaluare pre si postinterventionala, care sa cuprinda date despre parametrii biomecanici masurati prin intermediul unui sistem informatic de analiza kinetica a miscarii, parametrii care sa reflecte posbilitatile si potentialul functional al segmentului studiat in cadrul miscarilor ce permit independenta functionala a pacientului.

Crearea acestor modele bazate pe date obiective, rezultate din analiza computerizata a miscarii, permite alegerea unei interventii terapeutice tintite si eficiente si elaborarea unei baze de date accesibile unui numar mare de specialisti.

ETAPELE PROIECTULUI SI DATELE DE PREDARE

1. Managementul cercetarii si activitatilor suport ; 67650 RON ;  01/12/2006

2.  Achizitia datelor specifice cercetarii; 431900  RON; 01/11/2007

3. Investigatie imagistica si prelucrarea datelor obtinute prin SIMI Motion; corelare cu datele clinice si paraclinice ; 179303 RON ; 01/02/2008

4. Studii privind implementarea instrumentelor software; 351500 RON; 01/05/2008

5.  Validarea experimentala a metodologiei ; adaptare ; 271958 RON ;01/ 07/2008

6. Diseminarea finala  si exploatarea rezultatelor; 167239 RON; 01/08/2008

PROGRAMME: CEEX  P-CD

Name of the project:

Individualized management of mobility recovery  in  patients with neurological and orthopedic pathology by  interdisciplinary research methodologies

acronym: MANMOBREC

University Registration Number / Contract date: 107/2006

Module :     I

Director of project: Avramescu Taina

Partners: Spitalul Clinic de Urgenta MS  Curie, UMF Carol Davila, Universitatea Politehnica Bucuresti, IPA Bucuresti

Period: 01/08/2006- 01/08/2008

Budget: 1 469 550 RON

Summary:

The present project aims to analyse  the study of human motricity in normal and pathological conditions  (neurological and orthopedic pathology) by creation of a  laboratory for computational movement analyisis  which, with the help of interdisciplinary studies. will permit the elaboration of  pre and post interventional evaluation sheets including complex  information about biomechanical parameters measured  and the possibilities and functional potential of the studied segment, in order to assure functional independence of the patient.

The creation of these models, based on the objective results from the  computational  analysis of movement,  will help in choosing  the most  efficient therapeutically intervention  and creation of a data base  accessible to a great number of specialists.

SCHEDULE AND REPORT DEADLINES
1. Research and supportive activities management; 67650 RON ;  01/12/2006

2. Architectural system for research specific data acquisition; 431900  RON; 01/11/2007

3. Imagistic  investigations  and  processing  of  data  obtained by SIMI Motion analyse; corelations; with clinical and paraclinical parameters; 179303 RON ; 01/02/2008

4. Studies regarding implementation of software instruments; 351 500 RON; 01/05/2008

5.  Experimental validation of metodologiy; adaptation; 271 958 RON ;01/ 07/2008

6. Final disemination and   exploitation of  results; 167 239 RON; 01/08/2008