PROGRAM: CEEX

NUME PROIECT : SISTEM DE PROTECŢIA CULTURII DE RAPIŢĂ PRIN COMBATEREA INTEGRATĂ A BOLILOR, DĂUNĂTORILOR ŞI BURUIENILOR

Acronim: RAINCON

Numar de inregistrare la Universitate / Data contract: 385 / 04.10.2006

Modul :  I

Director proiect: Dr.ing. Nicolae VILAU

Parteneri: UNIVERSITATEA DIN CRAIOVA, SCDA SECUIENI, ICDPP BUCURESTI, UNIVERSITATEA BUCURESTI

Data incepere / finalizare proiect: 09.10.2006 / 15.10.2008

Valoarea proiectului: 1300 000 RON

Rezumat:

Proiectul are ca scop elaborarea, verificarea si integrarea unor mijloace de protectie intr-un sistem unitar, pentru protejarea culturilor de rapita impotriva a trei mari grupe de agenti de daunare : boli, daunatori si buruieni, care sa asigure obtinerea unor recolte stabile, sanatoase, concomitent cu protectia mediului inconjurator. Pentru indeplinirea lui se vor executa la nivel de laborator, camp experimental si statie pilot, activitati de experimentare a unor pesticide selective si biopesticide eficace si a unor amestecuri sinergice, care sa fie introduse in schema de protectie a culturii rapitei.

Prin respectarea masurilor agrotehnice optime, concomitent cu reducerea ponderii pesticidelor chimice, vor fi experimentate si mijloacele biologice prin utilizarea unor biopreparate pe baza de bacterii si ciuperci entomopatogene/antagoniste la tratamente la samanta si in vegetatie, pentru mentinerea principalelor boli si daunatori sub pragul economic de daunare.

ETAPELE PROIECTULUI SI DATELE DE PREDARE

1. Elaborarea si realizarea componentelor sistemului de protectie integrata a culturii rapitei / 169000 RON / 15.12.2006

2. Testarea componentelor sistemului de protectie integrata a culturii rapitei / 361 155 RON / 31.05.2007

3. Optimizarea componentelor de protectie integrata a culturii rapitei / 305 945 RON / 30.09.2007

4. Integrarea componentelor de protectie integrată a culturii rapitei / 290 997 RON / 31.05.2008

5. Testarea sistemului integrat de protectie integrata a culturii rapitei / 172 903 RON / 15.10.2008

PROGRAMME: Excellence Research CEEX

Name of the project : INTEGRATED PEST CONTROL OF SYSTEM OF RAPE CROPS

acronym: RAINCON

University Registration Number / Contract date: 385 / 04.10.2006

Module : I

Director of project: Dr.eng. Nicolae VILAU

Partners: UNIVERSITY OF CRAIOVA, SECUIENI AGRICULTURAL R&D STATION, BUCHAREST R&D INSTITUTE FOR PLANT PROTECTION, UNIVERSITY OF BUCHAREST

Period: 09.10.2006 / 15.10.2008

Budget: 1,300,000.00 RON

Summary:

The project have to elaborate, to verify and to integrate multi-components of protection into an unitary system for protecting the rape against three major groups of harmful agents: diseases, pests and weeds, that to assure the obtaining a constant, healthy crop along with the protection of the environment. For achieving the above objective a series of new selective experimental pesticides and bio-pesticides will be developed in the laboratory, experimental field and pilot stations and will be developed with into an integrated system to protect the rape crops. Simultaneously with a reduction in the chemical pesticides, experiments will be made following the optimal agrotechnical and biological measures that use bio-products based on enthomopathogenous bacteria and antagonistic fungus; treatments that maintain the major diseases and pests below the economical threshold.

SCHEDULE AND REPORT DEADLINES
1. Elaboration and realization of the integrated protection components of the  rape crop / 2006-12-15.

2. Testing of the rape crop integrated protection system components / 2007-05-31.

3. Optimisation  of the rape crop integrated protection system components / 2007-09-30.

4. Rape crop integrated protection system components integration / 2008-05-31.

5.  Rape crop integrated protection system testing / 2008-10-15.